## Sheet1
Questions to help you build a great project plan
A. Stakeholders
1. Who are my key stakholders?
2. What do they need to know?
3. When should I meet with them?
4. How should I best communicate with each of them?
5. What are my key deadlines in regard to them?
6. What needs to be in writing for them and by when?
B. Workshop content planning
1. What are the outcomes?
2. How long do I need to do the full workshop design?
3. Who needs to give me input into the design and by when?
4. Who will help me with a content and design review?
5. What pre-work do I need to plan?
6. What supporting materials will I need?
7. What does my sponsor need from me and when?
8. Who will give me a formal sign-off if I need it?
C. Logistics
1. Who should send out the Joining Instructions?
2. When do I send out the Joining Instructions?
3. How do I ensure everyone does any pre-work? Who checks?
4. What rooms do I need to book?
5. What equipment do I need to have?
6. How do I make sure wifi is available for everyone?
6. What breaks and refreshments have I planned?
8. Who will help me with AV?
9. When can I get into the room, and who's my point of contact for this?
10. Are there any public holidays/festivals around my selected dates?
D. Follow-up
1. What feedback will I collect and deliver to whom?
2. Who owns other follow-up actions?
3. How do we communicate follow-up actions and stay aligned?
4. Who needs to attend any workshop review and get feedback?
5. What's next?